## Slide 1: R.M. Schulze Family Heart and Stroke Critical Care Center Project Update
4.16.26

## Slide 2
Current Site Status &
Upcoming Work

## Slide 3
Foundation work nearing completion
Elevator and stair towers nearing completion
Underground utilities continuing
Structural steel erection started
Precast erection on parking garage starting up
Multiple active cranes onsite
Current Construction Activities

## Slide 4
Upcoming Work Activities
April
Start steel erection
Start parking garage precast erection
Complete Elevator C shaft
Complete foundations
Complete parking garage Stair A & Elevator A shafts
Continue underground utility work
Increase in trucking traffic
May
Continue steel erection & detailing of connections
Continue precast erection
Start slab on deck floor pours
Start sprayed fireproofing
Increase in trucking traffic
June
Continue steel erection & detailing of connections
Continue precast erection
Continue slab on deck pours
Continue sprayed fireproofing
End of month- Start exterior & interior wall framing

## Slide 5
Reasoning for NCH issuance of local resident project update letter
A request has been submitted to the city building dept for consideration on the following changes to construction work hours and days:
  Increase work hours onsite for steel erection from M-F 8am-4pm to 7am-5pm and allow steel erection to occur on Saturdays from May-August
  Start concrete deck pours in the early overnight hours of 2am from May-August
Benefits of proposed changes to the project & local residents:
  Reduces the number of concrete trucks on local roadways during normal business hours
  Completing the structural steel building frame prior to the onset of peak hurricane season
  Remove 2 of 3 large cranes onsite prior to the onset of peak hurricane season
  (3) week pick up on the duration of steel erection with additional work hours and days
  Noise mitigation strategies during early overnight work include:
    Changing backup alarms on concrete trucks from beeping to swoosh sounds
    Constructing a noise barrier / acoustic panel enclosure at concrete pump truck
    Use of battery powered equipment in lieu of gas powered where applicable

## Slide 6
What to expect over the next 3 months around the construction site

## Slide 7
What to Expect: May – July 2026
Increased construction vehicle traffic coming from 41 turning west on 2nd then into the jobsite – daily (concrete trucks, steel deliveries, precast deliveries, pump trucks, dump trucks, etc.)
Flagmen will be used to direct construction traffic entering and exiting the project site.
Cranes in operation onsite for precast panels and steel erection. Early overnight / morning concrete pours.
Precautions will be taken to minimize noise onsite during concrete deck pours during early work hours.
Local residents may hear a combination of horn or whistle sounds when the crane is actively hoisting loads across the site. This is an OSHA safety requirement for workers onsite.
An increase in onsite construction workers. A parking shuttle will continue to transfer construction workers from offsite parking areas to the construction site.

## Slide 8
Schedule Update

## Slide 9
Current Construction Schedule Milestones
(Subject to Change)
Parking garage
  Foundations complete – 2nd quarter 2026
  Precast structure erected – 3rd quarter 2026
  Building complete – 4th quarter 2026
  Landscaping installation – 4th quarter 2026
  (installation will occur in multiple phases)
Heart Vascular & Stroke Institute
  Foundations complete – 2nd quarter of 2026
  Fixed crane erected – 1st quarter of 2026
  Steel erection complete - 3rd quarter of 2026
  Exterior enclosed – 4th quarter of 2026
  Install elevators – 2nd quarter of 2027
  Permanent Power – 2nd quarter of 2027
  Commissioning of MEP Systems - 3rd quarter of 2027
  Building complete – 3rd quarter of 2027

## Slide 10
ALD - Ficus Tree Update
Site updates to maintain the tree during construction:
  Site retaining wall was moved back to benefit the root system
  Tree was treated for whiteflies
  Supplemental irrigation was added
  Tree has been trimmed per arborists recommendation’s
  Tree will receive additional trimming along boardwalk to correct a public safety issue with uneven load distribution
  Supplemental branch support will be added at several locations

## Slide 11
2nd Ave N Tree Improvements
  Replacing damaged & partial canopy mahogany trees w/ full canopy mahogany trees (3) total
  Reusing & replanting existing trees from the parking lots main drop off loop area
  Transplanted trees will provide a better full uniform canopy along the street line
ALD - Update on 2nd Ave N Tree line

## Slide 12
Lake updates
  New construction drainage outlet work is complete
  Winter temperature impacts to fish within the lake
  All work in and around the lake is performed within city and state requirements
  Evaluation and monitoring of lake conditions is ongoing
APEX - Lake Conditions

## Slide 14
Project Contact Information
Matt Holliday
neighbors@nchmd.org
239-826-7864
To learn more visit:
criticalcareinnaples.com

## Slide 15
THANK YOU